## Java-2018
Release Track
Sl. No | Date (MM/DD/YYY) | Developer Name & branch name | Module Name | QA Tag | QA Commit Id | Bug Ids | Task Ids | Remarks | Production Release Dt | Prod Tag | Prod Commit id | DB Changes | S3 Bucket | Config server Queries | Dependency Jars | Templates | New Environmental Variables Used
1 | 2018-07-12 |  | Appointment | QA_1.0.6_JULY11 | e252f655b6837da78f2b4929e54f89ba1041e8d0 | 1257
2 | 2018-07-12 |  | OPD | QA_1.10.9-JULY10 | 630b7c01a75b7a300aa54cf0bee3b71ca50632f8 |  |  | feature: adding api for fetch patient status details
3 | 2018-07-13 |  | Config Server / Architecture | QA_1.1.1_JULY12 | 7173f02e5e4b3f9825471e7d305de19909272b89 |  |  | Bug: Config server is not updating new addition to git if local git repo corrupted.
4 | 2018-07-13 |  | INVENTORY | QA_1.2_JULY13 | b4684f1719715b555e4ce4915107123c09cf9250 |  |  | RELEASED VENDOR INVOICE AND POINT OF SALE FUNCTIONALITIES
5 | 2018-07-11 |  | Communication | QA_1.2_JULY11 | 10d92641be17c6e377517d822323d86671a4a825 |  |  | alert sms for appointment
6 | 2018-07-10 |  | EMR | QA_1.7.3_JULY10 | a682488431497b67033e05b976f210c03dec8608 |  | ONE-T877 | OTP Authentication for EHR data retrieval
7 | 2018-07-13 |  | login | QA_1.4_July10 | ef226ad12dcffb9246df1b85c98164ebf55928d6 |  | ONE-T851 | OTP Authentication Functionality For Login
8 | 2018-07-13 |  | OPTICAL | QA_1.2_JULY13 | b4684f1719715b555e4ce4915107123c09cf9250 |  |  | RELEASED VENDOR INVOICE AND POINT OF SALE DUE PAYMENTS.
9 | 2018-07-14 |  | ERX | QA_1.01.00_JULY14 | 829ec8d345382ed00b936a6284d9d6b33b93d767 |  |  | I'm joined in query optical_item_ref with optical_inventory_trans while fetching brands in pos. Now API will fetch only inventory matched items only.
10 | 2018-07-14 |  | OPTICAL | QA_1.2.1_JULY13 | e24701cad644e6be22f271aa5d8176c8d3e90a18 | ONE-I1276
11 | 2018-07-14 |  | ERX | QA_1.01.00_JULY14 | 829ec8d345382ed00b936a6284d9d6b33b93d767 |  |  | Patient Status Flow Chart
12 | 2018-07-14 |  | Login | QA_1.4_July14 | ccbe16241c1a4f0dec0a62af5ce3d32d9bfedc38 |  | ONE-T851 | OTP Authentication Functionality For Login
13 | 2018-07-14 |  | Imaging | Qa_1.0.14.JULY | 9340aca93738bde9a1d3b52d0042fc40b2847cd3
14 | 2018-07-14 |  | optical | QA_1.2.2_JULY14 | 560c1521eb1aeedd12d1bf71f6179818422866b2 | 1278,ONE-I1276 |  | 1,VENDOR INVOICE FUNCTIONALITY 2,POINT OF SALE FUNCTIONALITY 3,BUG ID:ONE-I1276 4,BUG ID:1278
15 | 2018-07-16 |  | EMR | QA_1.7.4_July16 | 2f5ba211c47206be960799d5405454d9cbe84cb2 | 1290 |  | unble to save history tab
16 | 2018-07-19 |  | OPD | QA_1.11.11_JULY19 | 382a0148d147239a78f3aa5c3ac2517ccd835756 |  |  | New qa tag for changing http to https of api_usage_url
17 | 2018-07-19 |  | Website | Qa_1.0JULLY19 | 6c8cebb982d290a311e4925dea862ac1a14b2809 |  |  | websocket
18 | 2018-07-18 |  | communication | QA_1.3_JULY18 | f08c84d95d01d1b58a34eac4fbf1348827f5aab6 |  |  | Email file attachments
19 | 2018-07-21 |  | Reports | QA_1.1.1_JULY21 | 829f04289426b19a2ede695bcf5eb08eacaae14b |  |  | Added 1.fetchExpiredDrugDetailsJson 2.fetchPhramacyDrugwiseSalesJson 3.fetchPaymentModeWiseAdavanceCollectionJson 4.fetchAdvanceCollectionReportJson 5.fetchPatientVisitDetailsJson 6.fetchPharmacySalesReportJson 7.fetchHospitalWardOccupancyJson 8.fetchPharmacyCurrentInventoryJson and one pdf fetchPharmacyCurrentInventory
20 | 2018-07-21 |  | Quality | Qa_1.0JULLY21 | 354527beca17929874c679c103bd52c9cd82809a |  |  | added this new API for MIS report fetchMonthlyDataNew | 24th July 2016
21 | 2018-07-21 |  | billing | QA_1.11.13_JULY21 | f4fd52f5927b8edc9888b5ecd254c4c57865af20 | 1229,1228 |  | related to Insurance Bugs 1229,1228 | 24th July 2017
22 | 2018-07-21 |  | Insurance | QA_Insurance_1.0.3_JULY21 | d5e0334ea3f4b707eefaa4f9129d13d4a764e46f | 1229,1228,1015978 |  | Insurance bugs and add sql properties in mail | 24th July 2018
23 | 2018-07-23 |  | Website | Qa_1.1_JULLY23 | adad8acc6fb461f90cbc94111909513ce55809b2 |  |  | externalise the sql properties | 24th July 2018
24 | 2018-07-24 |  | opd | QA_1.11.15_JULY23 | b6438de0207b7cdf859f0d8e52b62561351b837a | 1331 |  | production bugs | 24th July 2018
25 | 2018-07-24 |  | billing | QA_1.11.15_JULY23 | b6438de0207b7cdf859f0d8e52b62561351b837a |  |  | service_qty data type change | 24th July 2018
26 | 2018-07-24 |  | Insurance | QA_Insurance_1.0.4_JULY24 | 147160d9eee0ab2a9f2f92d1c279892f99d5eab93 | 1345 |  | send hosPatientId instead of patientId | 24th July 2018
27 | 2018-07-27 |  | Login | Qa_1.4.3_27JULY | d162dd5b41706cc83eeafc2e9c22f93ae78a898a | 913,965,1004,1403 | ONE-T174 | 1.Ip restrcitions functionality 2.Fixed 3 bugs by Ram Mohan 3.Favourite screens functionality | 30th July 2018
28 | 2018-07-27 |  | Settings | Qa_1.0_30JULY | 0280f6509876aee26f424bb4afc8ce64d0901ed1 |  | ONE-T174 |  | 30th July 2018
29 | 2018-07-27 |  | EMR | QA_1.7.5_JULY27 | 59edd52e160cbc6603c6d9d194896ebab0a1ec15 | 1044 |  |  | 30th July 2018
30 | 2018-07-30 |  | OPD | QA_1.11.16_JULY30 | ffe827a8c19498ae76035713b06e51570c7248d1 | Bug not logged |  |  | 30th July 2018
31 | 2018-07-31 |  | Admin | Qa_1.5_31JULY | 6de0c1641f7f59e7dfb1becbbc04d5c98bba0e3c |  | ONE-T899 | landingpage | 14th August 2018
32 | 2018-07-31 |  | Website | Qa_1.1.1_JULLY31 | f411e3c9bbaef1fd4a01988b182a936af11eae0f | 1307 |  | upload file temp path issue | 14th August 2018
33 | 2018-08-01 |  | Admin | Qa_1.7_01AUG | 3a37986b7d1ba4ff1c39559d57a6ed5a46261aeb |  | ONE-T892 | Save print settings in Db | 14th August 2018
34 | 2018-08-02 |  | communication | QA_1.3.1_AUGUST2 | 56b5f70d06bd2f3de4b5c153fc1acc1641e3d72 | 1427 |  | Unable to sent mails for "non-dru.care" mails | 14th August 2018
35 | 2018-08-03 |  | billing,catalog | QA_1.11.18_AUG03 | ae246034772e50f8285c81f8e276cf821894facd | 1429, 564 |  | unable to save patient services(1429), mapped panels showing under avaliable panels(564) | 14th August 2018
36 | 2018-08-08 |  | EMR | QA_1.8_AUG08 | 250ae141d3bdc6bb989df9ce4b4e03d003bbdcf7 |  | ONE-T394 | Immunization Pricing | 14th August 2018
37 | 2018-08-08 |  | IPD | QA_1.0.8_AUG08 | 8cd3db90b197348b392e8a8cc405a3a3e0229f3c | 291, 1227 |  | unable to display bed name | 14th August 2018
38 | 2018-08-10 |  | Billing | QA_1.12.0AUG10 | a2065c70c690996ac144f6c477cc986cd1d8e5a2 |  | ONE-T907 | Due Payment History | 14th August 2018 |  |  | need DB changes in billing.patient_invoice_due_trans
39 | 2018-08-10 |  | Admin | QA_1.7_1AUG-BUGFIX1416 | f49a05c0f038404efdbf3ae2e314787c9d266184 | 1416 |  | landingpage | 14th August 2018
40 | 2018-08-10 |  | Ipd | QA_1.2.8AUG10 | 905fe2ffb2e649ac8ce1971a26c87f79b748275e | 1470 | ONE-T909 | OT_status | 14th August 2018
41 | 2048-08-14 |  | Admin |  | ef9d4638bc6ada6418f30eeb7359020e577cde12 | 1468 &1422 |  |  | 14th August 2018
42 | 2048-08-14 |  | Ipd | QA_1.2.10AUG14 | 6cb446702a0aca0ee8cacdf891bb0131f3d38c0e | 1470 |  | OT_status | 14th August 2018
43 | 2018-08-18 |  | Optical | QA_1.4_AUG18 | e0e2605724c01d49df775b94d4523b3638bc99f5 |  | ONE-T893 | Bar code generation if user not enter while saving items. And insert bar code settings. | 27th August 2018 |  |  | ..
45 | 2018-08-19 |  | Quality | Qa_1.2AUG19 | ff119a6c78df645c2a1e3456e1057e7ea99d99f1 |  | 1006 | added x-axis name and added order by based on month in fetchMonthlyDataNew api and indicators Data should be fetched sorted by date | 19th August 2018 |  |  | . | No | No | No | No
46 | 2018-08-19 |  | OPD,Billing | QA_1.12.1AUG19 | 1d166b0bd283fc04893b81998cdb57fb0d1c1c55 | 1499 |  | In case ward is de-allocate to that patient, then duplicate patient IDs are displaying |  |  |  | no | no | no | no | no
47 | 2018-08-20 |  | OPD | QA_1.12.2_AUG20 | 28f295f1a59ffac1050b68dd33d3b223a627ff95 | 1511 |  | Paid amount is not displaying in due payment history | 21st August 2018 |  |  | no | no | no | no | no
48 | 2018-08-20 |  | EMR | QA_1.9_AUG23 | f4991d933e82243c26ebb317274a87ad31e977d3 | 911 |  | Diagnosis wise Search | 27th August 2018 |  |  | no
49 | 2108-08-21 |  | Quality | Qa_1.2.1AUG21 | fd3a3ae6c0635a84938b6db6aa9a60f2e1a22a0f |  | 1012 | dept functionality has now been added to indicators. While entering indicators data, whatever department is selected, data will be retrieved only against that department. However, the total count in header is at organisation level. So if you add total for an indicator in one department, the same would also be visible for another department for same indicator. | 21st August 2018 |  |  | DB changes need
50 | 2018-08-24 |  | OPD | QA_1.13.AUG27 | e7c29dae068aabd3a5d97167605ae93a224525cd | No | ONE-T998 ONE-T718 ONE-T999 ONE-T1000 ONE-T1002 | Added digital board functionality | 27th August 2018 |  |  | DB changes need | No | No | No | No
51 | 2018-08-25 |  | Reports | QA_1.2.2_AUG25 | 0e6570fa4419e136c81d14f6c08c252bfa2a573f | ONE-I1544, ONE-I1543, ONE-I1545 | ONE-T901, ONE-T896 | Excel Report Functionality and pharmacy consolidate Report | 27th August 2018 |  |  | DB changes need | No | No | OPD(No need to do any changes) | No
52 | 2018-08-25 |  | Appointment | QA_1.0.7_AUG25 | 41f03893c9fa30eb5f6d2e81341c25b8d335b8ff | 881 | - | When slot settings were being done for a doctor, the specialties mapped to that doctor were getting deleted. This issue has now been fixed. | 27th August 2018 |  |  | No | No | No | No | No
53 | 31/08/2018 |  | OPTICAL | QA_1.4.2_AUG31 | b54e59ad311e5492dfa6962f851f7749357d8c49 | 1531 and 1450 | [5 empty] | No need DB Changes | No | Yes | No | No
54 | 31/08/2018 |  | Website | Qa_1.2_Aug31 | 28a0dccd93544b2f9491819dbb1cf690ed755d16 |  | ONE-T1013 | A Request for a Demo Form in website Home Page, with Mobile OTP Verification | 1st September 2018 |  |  | Db changes need | No | application.properties need to move | Communication need need to release to qa | Yes
55 | 2018-09-01 |  | Communication | QA_1.3.1_SEP1 | bd96b6edc203de1897ec32d12797a502729321f1 |  | ONE-T1013 | Changed Template name for Website module | 1st September 2018 |  |  | No Need | No | No | No | Yes
56 | 2018-09-02 |  | EMR | QA_1.13_Sep1 | 8432643d3242f11b30ed661fe312d96eb96f8107 |  | ONE-T232,T1010, T1011,T1016 | Counselling,Diagnosis wise Search with Emr,Dyanmic tabs, OPD status | 8th September 2018 |  |  | Need Db changes in Opd.patient_visit_trans and emr.org_tab_speciality_xref EMR.patient_opd_track_info_trans |  | queries and application properties need to move | Billing, IPD, OPD and Appointment jars |  | BILLING_IP ip address script
57 | 2018-09-02 |  | Billing and opd | QA_1.14.0SEP01 | 684c7eebe91f93093e6a13cc8598acf3eb154712 |  | ONE-T910,T1015 | opd+daycare patient allowed to billing,Opd status | 8th September 2018 |  |  | no | no | no | no | no
58 | 2018-09-01 |  | Appointment | QA_1.1.0SEP01 | bc20942149ee0135fcfa39faaf85571dd750b552 |  | ONE-T1022 | widget related code | 1st September 2018 |  |  | No | No | No | Website | No
59 | 2018-09-05 |  | OPD | QA_1.14.1_SEP5 | 684c7eebe91f93093e6a13cc8598acf3eb154712 |  |  | OPD status related linked to task | 8th September 2018
60 | 2018-09-05 |  | EMR | QA_1.13.1_SEP5 | d6b2a90a7cf9018a327deec2fde16cd493c72e55 | 1589 |  | OPD status related linked to task | 8th September 2018
61 | 2018-09-05 |  | OPD | QA_1.14.03SEP6 | bd10e0438b270cbb5b2685412459231c8dcb3a49 |  |  | OPD status related linked to task | 8th September 2018
62 | 2018-09-09 |  | OPD | QA_1.14.04_SEP7 | e54507ce2063387775ada900b51f1b4cea73f170 | 1589 |  |  | 8th September 2018
63 | 2018-09-09 |  | EMR | QA_1.13.1_SEP7 | 89393d78e7aa98b8dd95331780621e1dcf7880c6 | 1589 |  | OPD status related linked to task | 8th September 2018
64 | 2018-09-09 |  | EMR | QA_1.13.2_SEP7 | dfe9278028304c3c850efb76b978f404b0879bca | 1600 |  | OPD status related linked to task | 8th September 2018
65 | 2018-09-09 |  | Reports | QA_1.3.0SEP07 | 529404ccccbb880bc9f1db8698df78323bb22baa |  | 896,1043 | Lab diagnosis report and pharmacy sold report | 8th September 2018
66 | 2018-08-09 |  | Ipd | QA_1.2.28SEP |  | ONE-I1559, I1558, I1557, I1486, I1483, 1482,1474,1455, 1399, 1323, 1223, 1028, 1027, 964,963,886,1441 |  | These mainly related to the bedallocation deallocation and bedshifting . While allocation ,deallocation and shifting bedenquiry details are not changing
67 | 14/09/2018 |  | Appointment | QA_2.0SEP14 | e26ffc74dcfa467d6e9d37c143caaed574ed176e |  | ONE-T1036 | Filters added for widget functionality | 14th September 2018 |  |  | Yes. Need to do | No | No | No | No
68 | 18/09/2018 |  | Communication | QA_1.3.2_SEP18 | 7af0480ed8b22ef6d47098df64251066732938a3 | No |  | Communication Module Change the old URL to new URL | 19th September 2018 |  |  | NO | NO | NO | NO | NO
69 | 28/09/2018 | dev | Ipd | QA_1.2.3.SEP28 | b94362a654ab08273f35675cf57cd8a0c00cb844 | 1735 |  | In Ipd module in bed Enquiry screen ipd not displaying we fix that bug | 28th september 2018 |  |  | no | no | no | no | no
70 | 26/09/2018 |  | LAB | Qa_1.0.1_SEP26 | 0aac6839326c5ad3cf552ca2234cd0cb307b3826 | 1603 |  | For Lab print functionality in query screen | 26th September 2018 |  |  | Yes. Need to do
71 | 2018-10-01 |  | IMAGING | Qa_1.0.1OCT1 | 475352dc1610cc174d3f2d560f812d642a353fde | 1709 1707 |  | 1709 1707 fixed this bugs |  | Prod_1.4.0OCT1 | a2e582858f694d64e69c15109af8ae6a1f817554 | No | No | No | No | No
72 | 2018-01-10 |  | Reports | QA_1.4.0OCT1 | c12a2d52675d08b8a0b56ddb12aedc8d2b51e3e4 |  | 1063 | Pharmacy profit report released | 1st September 2018 | Prod_1.4.0_OCT1 | 927c68647dd89cfc86f79ec4f6f3180dc32f108d | Yes. need to add report URL in screen_ref tabel | no | no | no | no
73 | 2018-05-10 | Sireesha/temp | IPD | QA_1.2.8_OCT5 | 86d175af6a14bf1981d123bdf28362c559da851c | 1660,1557,1482,1455 | ONE-T1032 | ward And OT Refactoring And Bug Fixes |  |  |  | no | No | yes | no | no
74 | 2018-06-10 | Ram Mohan Reddy | Emr |  |  | 1787 |  | Not Working For Some Accounts In Qa
75 | 2018-08-10 | Ram Mohan Reddy/T1054 | Emr | QA_1.10_OCT08 | f17212cca9abb48a7c15ae20108df392c3ef7d3c |  | ONE-T1054 | hard coded values |  |  |  | Yes |  | yes | no | no
76 | 2018-09-10 | Vivitha/Tejaswi -Dev | OPD | QA_2.1.2OCT9 | 45c3d66708f1d59bb5d96d6abeb61be60c0a4782 | 1806,1808,1782 |  | Bug fixes | 9th October 2018 | Prod_2.1.2OCT | b4bb8178e153e8c80f657448f3d78053e9dd1877 | No | NO | No | No | No
77 | 2018-10-10 | vivitha-commonReg | app-core | QA_1.0.0_OCT12 | ab7fada443c4df6d64e2ccf3dba9efa61ba1b2e4 | 1825 |  | Bug Fix | 2018-10-11 |  |  | No | No | No | No | No
78 | 2018-11-10 | Ram Mohan Reddy/dev | website | QA_1.3_OCT11 | 3175f703c9739c45bc2d680039b538188d77b0bc |  |  | for patient portal template format changed |  |  |  | no | no | no | no | yes/TEMPLATE_PATIENT_PORTAL_SIGNUP_SMS
79 | 15/10/2018 | sireesha/T1073 | IPD | QA_1.2.10_OCT15 | c9741feb5b7580c1816bb8b38cc8a8e20317b1df | 1830 | ONE-T1073 | Ward And Ot Related DB changes |  |  |  | Yes | NO | Yes , nursing care | No | NO
80 | 13/102018 | Ram mohan Reddy | EMR |  |  | 1840(prod bug) |  | If User Have Access Of EMR But The Data Not Saved By User |  |  |  | no | no | no | no | no
81 | 17/10/2018 | Vivitha/Tejaswi - ONE-I1812 | OPD | QA_2.3.12OCT17 | ec6bd78baf5f07cfcae1af8b0349eb15844c54c9 | ONE-I1865 ONE-I1834 ONE-I1813 ONE-I1771 ONE-I1757 ONE-I1747 ONE-I1711 ONE-I1693 ONE-I1654 ONE-I1653 | ONE-T903 ONE-T905 | Common Registration related bugs and name based search |  |  |  | No | No | No | No | No
82 | 17/10/2018 | Sireesha -b1861 | IPD | QA_2.3.12OCT17 | bb0db7b2a9191f46e85e0595c88236c8eb5e38ad | ONE-I1861 |  | In ward and Ot module added another keys relationship and change api bedAllocation | er Building |  |  | Yes |  |  | Nursing-Care
83 | 17/10/2018 | Manmadha | Reports | QA_1.4.1_OCT17 | 6f7afa918a1816db2a0580e7daa51b5f9750cbfe | ONE-I1862 | ONE-T1102
84 | 22/10/2018 | Rama Mohan Reddy/dev(T1079) | EMR | QA_1.14.0_OCT22 | d094bc443539fe467ce1d2937a0751226f74ddb7 |  | ONE-T1079 | Retinoscopy --->New component Chief complaints --> new component for only ophthalmology past medical history (replacement of Systemic History) --> adding Duration and duration units ophthalmic history---> new component (we are capturing glaucoma in this component and past medical history. but we are not able to capture it from past medical history) Contact Lens Prescription ---> New component Allergies --> New component Keratometry ---> New component Refraction(Dilated) ---> Existed component(Adding drug used for left and right eyes as an individual field) PMT ---> New component Glasses Rx ---> Existed component(Adding new lens data) Color vision,Intraocular pressure,Contrast sensitivity Task Information | 2018-10-24 | Prod_1.14.0_OCT24 | 50d636ecf65a3fad6d5c4215e2a8b2b7693ee04c | yes | no | yes | no | no
85 | 23/10/2018 | Manmadha | Reports | QA_1.4.3_OCT17 | 89140954814535892b2844fd873c0eeddafbac0b | 1899, 1900 |  |  |  | Prod_1.4.3_OCT17 | 89140954814535892b2844fd873c0eeddafbac0b
86 | 24/10/2018 | Sireesha/B1898 | Nursing Care | QA_1.2.12_OCT_26 | acc82bf58dbf634dcfc769e79d449e0dea86cab2 | 1898 |  | In Nursing Care patient was not discharged API is failed Due to Query Problem | 2018-10-24 | Prod_1.2.12_OCT_26 | acc82bf58dbf634dcfc769e79d449e0dea86cab2 | NO | NO | YES | Nursing-Care | NO
87 | 29/10/2018 | vivitha/commonreg_billing_bugs | OPD | QA_2.4.26_OCT29 | 9d6163dac3d655334c741b9ee91e1f95accc1419 | ONE-I1991, ONE-I1988, ONE-I1986, ONE-I1980, ONE-I1979, ONE-I1976, ONE-I1969, ONE-I1958, ONE-I1955, ONE-I1922, ONE-I1903, ONE-I1902, ONE-I1901, ONE-I1894, ONE-I1889, ONE-I1882, ONE-I1837, ONE-I1812, ONE-I1809, ONE-I1790, ONE-I1781, ONE-I1764, ONE-I1751, ONE-I1745, ONE-I1743, ONE-I1721 | ONE-T1101 | Bug fixes in commonReg and print related changes in OPD and billing | 2018-10-29 | Prod_2.4.26_OCT29 | 9d6163dac3d655334c741b9ee91e1f95accc1419 | NO | NO | YES | Billing(Same as OPD commit and tag name) | No
88 | 29/10/2018 | Chaitanya | Pharmacy | QA_1.8_OCT29 | 1f0bfd336471f93f811f7ae3469461c94ecc33e3 | 1965 | 1120 | Pharmacy POS report modifications. | 2018-10-29 | Prod_1.8_OCT29 | 1f0bfd336471f93f811f7ae3469461c94ecc33e3
89 | 29/10/2018 | Manmadha | Reports | QA_1.6.1_OCT29 | b3058ab173b532ee4044737ded7d7d6092729ae7 | 1766 | 1121 | POS returns bug fix | 2018-10-29 | Prod_1.6.1_OCT29 | b3058ab173b532ee4044737ded7d7d6092729ae7
90 | 2018-01-11 | Rama Mohan Reddy | emr | QA_1.14.11_NOV03 | b4e93847925a14bdbf6db1b7af6e50074f159ae7 | 2001,1999 ,1566 ,1542 ,1350 ,1136 , 969, 928, 883, 833, 670 |  | Need to move two templates TEMPLATE_TEMP_PASSWORD_EMAIL_LINK_EMAIL.vm TEMPLATE_TEMP_PASSWORD_EMAIL_LINK_SMS.vm | 2018-03-11 | Prod_1.14.11_NOV03 | fe95ce4695ace31355c4a38831509feb96308d6b | YES | NO | YES | Billing | YES TEMPLATE_TEMP_PASSWORD_EMAIL_LINK_EMAIL.vm TEMPLATE_TEMP_PASSWORD_EMAIL_LINK_SMS.vm
91 | 31/10/2018 | Manmadha | Reports | QA_1.6.3_OCT31 | b0fe34021b4373ab29ae7c1f82964fe6fcdc7da6 |  |  |  |  | Prod_1.6.3_OCT31 | 95028fbbf5cbdca61c8bdf9bf8372ce63b6386b0
92 | 2018-11-03 | Sireesha | Ipd | QA_1.2.24_NOV03 | 2db0ebad48f7b56972affc71d4b221d8ec6eee48 | 1888,1870,1861,1859,1845,1831, 1830,1730,1660,1120. |  |  | 2018-11-03 | PROD_1.2.24_NOV03 | 852cff41f6007066fd924bdf2caa2f01b03a72b8
93 | 2018-01-11 | Tejaswi | Billing | QA_2.4.27_NOV03 | 140a7c53eb156946258a98bf2c4bac9014da9fdf | 2057 | 1126 | Counselling related changes. | 2018-03-11 | Prod_2.4.27_NOV03 | e3037a401ec9cb64456f3fd673ee378daa6d27db | No | No | No | No | No
94 | 2018-08-11 | vivitha | opd | QA_2.4.55_NOV08 | e8c52ce8fd82449af6fe131583329f0eff74555b | ONE-I2086,ONE-I2083,ONE-I2079, ONE-I2069,ONE-I2048,ONE-I2042, ONE-I2036,ONE-I2032,ONE-I2030, ONE-I2029,ONE-I2028,ONE-I2021, ONE-I2020,ONE-I2019,ONE-I2009, ONE-I2007,ONE-I1996,ONE-I1981, ONE-I1948,ONE-I1923,ONE-I1904, ONE-I1875,ONE-I1815,ONE-I1752, ONE-I1749,ONE-I1514,ONE-I1320, ONE-I381 |  | opd module bug fixes | 2018-10-08 | Prod_2.4.55_NOV08 | 367c3b10d2dbeb76282af003385fdde6c640f2c3 | No | No | No | No | No
95 | 2018-08-11 | Chaitanya | MIS(Reports) | QA_1.4.0_NOV08 | fc810d35c949840ac9846c286a8c29bfe36150a2 | I2044 | ONE-T1132 | Handled Due deduction POS returns report, Rounded amounts in All revenue related MIS queris. | 2018-10-08 | Prod_1.4.0_NOV08 | 13a84bfc7db066b6c6fe79d2c457124f9c6563a4 | No | No | No | No | No
96 | 2018-09-11 | Tejaswi/admin_bugs | Admin | QA_1.7.2_NOV09 | 4653871d6307c153ae2fefcfb93fc992382f7ed7 | 1750 and 374 |  | Admin bug fixes | 2018-11-09 | Prod__1.7.2_NOV09 | b68a28d587bc598065e7ff42a46204b5ac67518f | No | No | No | No | No
97 | 2018-10-11 | Sireesha Kakumanu | SMS | QA_1.1.2_NOV10 | 49eb128c6f5ccf90a239c106eacf417a108ad194 | I2065 and I1896 | T1113
98 | 2018-12-11 | Chaitanya/optical_06-06-2018 | Optical(Inventory) | QA_1.5.7_NOV12 | da0b9b227cc12ba9fa43ed3943b886ae54524511 | 1993, 2089, 2116, 2016, 1927, 1926, 1776 | T1141 | Added new functionalities to add user custom master data and Bug fixes. | 12th November 2018 |  |  | public.optical_masters_ref table with Orgid 1 all Data | No | Yes | No | No
99 | 2018-12-11 | Sireesha / B1911 | Website | QA_1.3.2_NOV12 | 23f23c78f5003c021589e95c42ca2c991790e10b | 1908,1911 | [6 empty] | No | No | No | Yes, TEMPLATE_REQUES…FOR_DEMO_EMAIL.vm
100 | 13/11/2018 | vivitha/ONE-T1145 | opd |  | f4bfaf09bac740015735225c0c160bf05058231c |  | ONE-T1145 | Added sms for newly registered patients in common registration | 13th November 2018 |  |  | not required | No | No | No | yes.PATIENT_REGISTRATION_SMS
101 | 13/11/2018 | Manmadha/T-1146-1147-1148-1149 | Reports |  |  | I2163 | ONE-1146 | Fixed the format of Lab consolidated Report and Added User Wise selection filter In Day wise Admission report |  |  |  | Inserted empId field into report_inputs_info_ref for Day Wise admission Screen | No | No | No | No
102 | 14/11/2018 | Manmadha/MIS-I2184 | MIS(Reports) | QA_1.4.1_NOV14 | 4cadff161a78e9ae23805dc5aa993f7ecdc3c58e | I2184 | No | changed API names to fetchOrgGrpWiseOPDCollection, fetchOrgWiseOPDCollections | 14th November 2018 |  |  | Not required | No | No | No | No
103 | 16/11/2018 | Ram Mohan Reddy/T1079 | EMR | QA_1.14.41_NOV16 | 388b177036e719eacafdcc18b126d73aba087879 | 2080,2077,1802,1791,1556,1550,1383,1538,1329,1116,915,825,750,1131,1172,1202,1216,1256,1267,1343,1381,1463,1567,1678,1706,1807,1848,1849,1880,1881,2018,2064,933,1032,1046,1059,765 | 1079 | Bug fixes and Eye Examination new Component and Summary Print Changes in Ophthalmology Specialty | 17th November 2018 | Prod_1.14.41_NOV16 | 40943b76dab4104c851f7cc099ec6f367653ef2e | yes(Examination relared and bugs and examination script) | no | yes | no | no
104 | 16/11/2018 | Sireesha | Nursing Care | QA_1.2.26_NOV16 | f05decfa7d1151d0531df8f2049531f081825c55 | 1597 |  | bug Fixes | 17th November 2018 | Prod_1.2.26_NOV16 | b894eafe834fb27b27d0721094cc1770472e9fc4 | not required | no | no | no | no
105 | 16/11/2018 | Sireesha | IPD | QA_1.2.26_NOV16 | f05decfa7d1151d0531df8f2049531f081825c55 | 2208 |  | bug Fixes | 17th November 2018 | Prod_1.2.26_NOV16 | b894eafe834fb27b27d0721094cc1770472e9fc4 | not required |  | no |  | no
106 | 16/11/2018 | Ram mohan Reddy/T1113 | Promosms | QA_1.1.4_NOV16 | 1185c77ac2303dfe2d5e00537b6781fa7ae094d3 | 2066,2063 | 1133 | bug Fixes and 1.clear function when excel upload a file 2.Select count, total count Of Patients when the patients search with filters like department, Groups...etc 3. In Grid, we are showing Patient Details like patine id, gender,name,department ...etc when patients search with filters like department,groups...etc | 17th November 2018 | Prod_1.1.4_NOV16 | d73f9960a3d1f94c1e741ab1ccaa1feb6070a4fa | not required | no | no | no | no
107 | 16/11/2018 | Ram mohan Reddy/T1122 | ERX | QA_1.1.10_NOV16 | 243e32426891d517286dfbd8a995b2c702ff29ef | 2084,1939.1938,1935,1710,1513,1458,1288,905,419 |  | Bug Fixes | 2018-11-17 | PROD_1.1.10_NOV16 | 243e32426891d517286dfbd8a995b2c702ff29ef | not required | no | no | no | no
108 | 2018-11-21 | Chaitanya | Optical(Inventory) | QA_1.6.0_NOV21 | 6ea3feaa9f97f91c7cd652aa2952bce241a79b3c |  | T1168 | Handled optical item master data update inventory item wise. | 21st November 2018 | Prod_1.6.0_NOV21 | 6ea3feaa9f97f91c7cd652aa2952bce241a79b3c | Yes | no | yes | no | no
109 | 22/11/2018 | Manmadha/T-1161 | Reports-MIS | QA_1.6.0_NOV22 | fe8cee73009fbee0a4dbb6f1cf7df28ef2ec7ee2 |  | T1161, T1149 | Restricted Data showing for sub branches if only super admin will see all the branches data in MIS and added advane amount in Day wise discharge report | 22nd November 2018 | Prod_1.6.0_NOV22 | f9432eb4909577fcc68a19f241874dd7e3369a99 | Not required | No | No | No | No
110 | 23/11/2018 | Chaitanya | Pharmacy |  |  | Bugs are more than 35 | 1153 1154 | doctor drop down added in POS. Fixed many Bug's. |  |  |  | Not required | No | yes | No | No
111 | 23/11/2018 | Manmadha | Reports |  |  |  | T1147 | added time pick's |  |  |  | Not required | no | no | no | no
112 | 24/11/2018 | Manmadha/T-1161 | Reports |  |  |  | T1147 | from date and to date will come with time |  |  |  |  | No | No | no | no
113 | 27/11/2018 | Manmadha/T-1161 | Reports |  |  | I2302 | T1175 | Implemented Opd consultaion report with new format and upadated day wise discharge report in ascending order. |  |  |  | No | No | No | No | no
114 | 27/11/2018 | Tejaswi/insurance-bugs | Insurance | QA_1.0.12_NOV30 | 0b103a62747fedaa61b3118ce335fe16dd2bd2cb | 1353,1354,1921,2025,2153,2114,1000,999,998 |  | Bug fixes | 30th November 2018 | Prod_1.0.12_NOV30 | 0b103a62747fedaa61b3118ce335fe16dd2bd2cb | Yes | No | Yes | No | No
115 | 27/11/2018 | Tejaswi/Billing_bugs | OPD,Billing,catalog |  | 76c601bedb021653b31a6613204f5ca3c2781a56 | 1877,1844,1842,1731,1530,2170,2168 |  | Bug Fixes | 30th November 2018 |  |  | No | No | No | No | No
116 | 27/11/2018 | Tejaswi/userManagement_bugs | Admin | QA_1.7.6_NOV30 | 96f03bdb1f810bf399af51e44682b63a076ec245 | 2136,2085,784,2311 |  | Bug fixes | 30th November 2018 | Prod_1.7.6_NOV30 | 3c0fc5078a1d14488fe9431a291530bc60ff7330 | No | No | No | No | No
117 | 2018-11-30 | chaitanya | Pharmacy |  |  | I2320, I2328 | No | Bug fixes |  |  |  | No | No | Yes | No | No
| 2018-12-01 | Tejaswi/ONE-I2332-billtype | OPD | QA_2.4.63_DEC1 | 786a54a9595c0e422b738005aa4c62b97c07422e | ONE-I2332 | No | Bug Fix | 1st December 2018 | PROD_2.4.63_DEC1 | 786a54a9595c0e422b738005aa4c62b97c07422e | No | No | No | No | No
119 | 2018-12-01 | vivitha/ONE-T1187 | Billing | QA_2.5.0_DEC1 | a44c4e40c2461c77e011cc1d2239d9a0f829a4e8 | no | ONE-T1187 | in print we are only showing service instead of serviceNm+doctoename for consultation services | 1st December 2018 | PROD_2.5.0_DEC1 | a44c4e40c2461c77e011cc1d2239d9a0f829a4e8 | No | No | No | No | No
120 | 2018-01-12 | Manmadha/MIS-T1161 | Reports |  |  |  | T1185,T1186,T1177,T1178 | added time pickers in some reports, modified lab sales repor and written two new reports. |  |  |  | yes | No | No | No | No
121 | 2018-06-12 | manmadha/mrpbranch | Reports |  |  |  | T1189 | For getting imaging tests along with lab tests i added condition in query of consolidated daignosis report |  |  |  | No | No | No | No | No
122 | 2018-06-12 | Sai Naresh/lab_new_functionality_03_nov | Lab | QA_1.2.5_DEC08 | cc29c422b535098b6c924bfb08dc286cacb55402 | ONE-I2307,ONE-I2178,ONE-I2072,ONE-I2070,ONE-I2068,ONE-I2053,ONE-I2050,ONE-I1835,ONE-I1738,ONE-I1970,ONE-I1132 | ONE-T1133,ONE-T1134,ONE-T1135,ONE-T1136,ONE-T1137,ONE-T1138,ONE-T1139,ONE-T1140 | new functionality in all the screen with panel mapping and order wise handling.and test reference values | 08th December 2018 | Prod_1.2.5_DEC08 | eb6d31c6cb0e97401f0b133e6e08c9aef1855a8c | Yes |  | Yes
123 | 2018-08-12 | vivitha/tejaswi/ONE-T1167 | opd | QA_2.6.0_DEC08 | 09789d82f5d1235d2a788bc2ebd08e85d5ea1ed0 |  | ONE-T1167 | for this we merged opd+billing+catalog+insurance jars | 08th December 2018 | Prod_2.6.0_DEC08 | 09789d82f5d1235d2a788bc2ebd08e85d5ea1ed0 | no | No | Yes For this need to create sql and application.propertief file for qa | No | No
124 | 2018-08-12 | Manmadha/mrpbranch | Reports |  |  | I2299 |  | added from date and to date filters in patient balance due report and modified laboratory report |  |  |  | Yes | No | no | No | No
125 | 2018-11-12 | Tejaswi/invoice-issue | OPD | QA_2.6.1_DEC10 | dea4c8b1a0443e0c202e727d77ff1f418020f12d | I2332 |  | Removed IPD_NO not null condition in on Api | 10th December 2018 | Prod_2.6.1_DEC10 | 7db3a193a8ce77c12fbdeaaab78051c36dbdaf24 | No | No | No | No | No
126 | 2018-11-12 | Tejaswi/vivitha/invoice-issue | OPD | QA_2.6.3_DEC11 | ca62125b35f498bf0851ce97b1db71448d0793ba | 2388 and 2392 |  |  | 11th December 2018 | Prod_2.6.3_DEC11 | 8c71865a18b0b003d7f62c1ce91380c4c1145062 | No | No | Yes For this need to create sql and application.propertief file for qa | No | No
127 | 2018-12-14 | Sai Naresh/lab_new_functionality_03_nov | LAB |  |  | I2371, I2401 , I2411, I2412 and I2416 |  | Bug Fixes |  |  |  | No | NO | No | No | No
| 13/12/2018 | Tejaswi/invoice-issue | OPD | QA_2.6.5_DEC13 | 1a3e90147af2c3280dab765c21e11b5db7ab9069 | I2382,I2408 |  | Bug Fixes | 13th December 2018 | Prod_2.6.5_DEC13 | 361c1b7535e99d3a60204b4ab48610091fb52e2c | No | NO | Yes | No | No
128 | 2018-12-14 | Chaitanya/23-10-2018-bug-fixes | Pharmacy |  |  | ONE-I2361 ONE-I2316 ,ONE-I2338 ,ONE-I2337 ,ONE-I2336 ,ONE-I2335 ,ONE-I2281 ,ONE-I2274 ,ONE-I2096 | T1127 T1129 T1170 | Pharmacy returns new functionality added. |  |  |  | Yes |  | Yes | App-core
129 | 2018-12-14 | Manmadha/mrpbranch | Reports |  |  |  | T1117, T1196 | Modified Pharmacy Returns Slip print with new format and adjusted alignment of tests and panels in Lab order query print |  |  |  | No | No | No | No | No
130 | 2018-12-15 | Chaitanya | Pharmacy |  |  | Bug id: 2419 |  | Added new key in pos retuns api |  |  |  | No | No | No | No | No
131 | 2018-12-15 | Ram Mohan Reddy | SMS |  |  | 2402,2318,2314,1985 | [5 empty] | yes | no | no | no | no
132 | 2018-12-15 | Sirisha | EMR |  |  | 2348 ,2347 ,2346 ,1960 ,1032 ,324 ,319 | [5 empty] | yes | no | no | no | no
133 | 2018-12-15 | Sirisha | IPD | QA_1.2.31_DEC18 | 2940a2847f0ab1107c584c0cc696782818abac5a | 2257,1027,2194,2144,2143. |  |  | 18th December 2018 | Prod_1.2.31_DEC18 | 4607ce7c0ce8f4792124c593f7819c2dc046e805 | yes | no | no | no | no
134 | 2018-12-18 | Sai Naresh/lab_new_functionality_03_nov | Lab |  |  | I2438,I2430 |  | added new key in updateTestStatusAndImagePath api |  |  |  | Yes |  | Yes
135 | 2018-12-18 | manmadha/MIS-T1161 | Reports |  |  | I2299 | T1212 | Fixed bug id: !2299 i.e added org details for some reports.Updated lab order query print i.e seperated Units as seperate column and added order date with time |  |  |  | No | No | No | No | No
136 | 2018-12-18 | RamMohan/Sireesha/ ONE-T1208 | OPD | QA_2.8.0_DEC22 | 1b141e01b4043d269b6581df1c64d6622958954c |  | T1208,T1210 | Added Email triggering for deleting Invoices and changing prices in catalg | 22nd December 2018 | Prod_2.8.0_DEC22 | 06ad6ca65133fbc5bd920f32b658eea9b0721517 | No | No | No | No | Yes INVOICE_DELETE_EMAIL​ ​TEMPLATE_CATALOGUE_PRICE_CHANGES
137 | 2018-12-28 | Sai naresh/lab_new_functionality_03_nov | Lab |  |  |  | T1216 | Added new logic for fetching the test references for both numeric and non-numeric test results |  |  |  | Yes |  | Yes |  | No | No
138 | 2018-12-28 | manmadha/MIS-T1161 | Reports |  |  | I2478 |  | updated bill_type='IPD-FINAL-BILL' field in day wise discharge report query for showing final bill when patient discharged. |  |  |  | No | No | No | No | No
139 | 2018-12-28 | Vivitha/ONE-T1478-Emr | OPD | QA_2.10.30_DEC28 | 94cde6d839b9adb511ddf326274137754800dee0 | I2340,I2323,I2280,I2271, I2270,I2266,I2265,I2242, I2232,I2187,I2182,I2160, I2154,I2149,I2142,I2137 I2135,I2120,I2112,I2111 I2109,I2108,I2041,I2007 I2006,I1923,I1742,I381 ,I1768 ,I2414 | ONE-T904 ONE-T1158 | Bug fixes from Ui and EMR related code and referral type tasks | 28th December 2018 | PROD_2.10.30_DEC28 | 4f9a186aeddbbba8b5f2d7c563bb2c8218b23cc7 | Yes | No | Yes | No | No | No

## UI
Sl. No | Date (MM/DD/YYY) | Module Name | Developer Name / branch name | QA Tag | QA Commit Id | Production Release Dt | Prod Tag | Prod Commit id | Remarks
Date(MM/DD/YYY) | Developer
Prod Tag | Prod Commit id |  | Module Name | Task Ids | Remarks
DB Changes | S3 Bucket |  | Config server
Dependency
Templates
2018-07-12 |  |  |  | e252f655b6837da78f2b4929e54f89ba1041e8d0 | 1257
2018-07-12 |  |  |  | 630b7c01a75b7a300aa54cf0bee3b71ca50632f8
2018-07-13
QA_1.1.1_JULY12 | 7173f02e5e4b3f9825471e7d305de19909272b89
2018-07-13 |  |  |  | b4684f1719715b555e4ce4915107123c09cf9250
2018-07-11 |  |  |  | 10d92641be17c6e377517d822323d86671a4a825
2018-07-10 |  |  |  | a682488431497b67033e05b976f210c03dec8608
2018-07-13 |  |  |  | ef226ad12dcffb9246df1b85c98164ebf55928d6
2018-07-13 |  |  |  | b4684f1719715b555e4ce4915107123c09cf9250
2018-07-14 |  |  |  | 829ec8d345382ed00b936a6284d9d6b33b93d767
2018-07-14 |  |  |  | e24701cad644e6be22f271aa5d8176c8d3e90a18 | ONE-I1276
2018-07-14 |  |  |  | 829ec8d345382ed00b936a6284d9d6b33b93d767
2018-07-14 |  |  |  | ccbe16241c1a4f0dec0a62af5ce3d32d9bfedc38
2018-07-14 |  |  |  | 9340aca93738bde9a1d3b52d0042fc40b2847cd3
2018-07-14 |  |  |  | 560c1521eb1aeedd12d1bf71f6179818422866b2 | 1278,ONE-I1276
2018-07-16 |  |  |  | 2f5ba211c47206be960799d5405454d9cbe84cb2 | 1290
2018-07-19 |  |  |  | 382a0148d147239a78f3aa5c3ac2517ccd835756
2018-07-19 |  |  |  | 6c8cebb982d290a311e4925dea862ac1a14b2809
2018-07-18 |  |  |  | f08c84d95d01d1b58a34eac4fbf1348827f5aab6
2018-07-21 |  |  |  | 829f04289426b19a2ede695bcf5eb08eacaae14b
Srinivas Nangana
2018-07-21 |  |  |  | 354527beca17929874c679c103bd52c9cd82809a
2018-07-21 |  |  |  | f4fd52f5927b8edc9888b5ecd254c4c57865af20 | 1229,1228
2018-07-21 |  |  |  | d5e0334ea3f4b707eefaa4f9129d13d4a764e46f | 1229,1228,1015978
2018-07-23 |  |  |  | adad8acc6fb461f90cbc94111909513ce55809b2
2018-07-24 |  |  |  | b6438de0207b7cdf859f0d8e52b62561351b837a | 1331
2018-07-24 |  |  |  | b6438de0207b7cdf859f0d8e52b62561351b837a
2018-07-24 |  |  |  | 147160d9eee0ab2a9f2f92d1c279892f99d5eab93 | 1345
2018-07-27 |  |  |  | d162dd5b41706cc83eeafc2e9c22f93ae78a898a | 913,965,1004,1403
Tejaswi | 30th July 2018
2018-07-27 |  |  |  | 0280f6509876aee26f424bb4afc8ce64d0901ed1
2018-07-27 |  |  |  | 59edd52e160cbc6603c6d9d194896ebab0a1ec15 | 1044
2018-07-30 |  |  |  | ffe827a8c19498ae76035713b06e51570c7248d1 | Bug not logged
2018-07-31 |  |  |  | 6de0c1641f7f59e7dfb1becbbc04d5c98bba0e3c
2018-07-31 |  |  |  | f411e3c9bbaef1fd4a01988b182a936af11eae0f | 1307
2018-08-01 |  |  |  | 3a37986b7d1ba4ff1c39559d57a6ed5a46261aeb
2018-08-02 |  |  |  | 56b5f70d06bd2f3de4b5c153fc1acc1641e3d72 | 1427
2018-08-03 |  |  |  | ae246034772e50f8285c81f8e276cf821894facd | 1429, 564
samba | 14th August 2018
2018-08-08 |  |  |  | 250ae141d3bdc6bb989df9ce4b4e03d003bbdcf7
2018-08-08 |  |  |  | 8cd3db90b197348b392e8a8cc405a3a3e0229f3c | 291, 1227
2018-08-10 |  |  |  | a2065c70c690996ac144f6c477cc986cd1d8e5a2 |  | need DB changes in
2018-08-10 |  |  |  | f49a05c0f038404efdbf3ae2e314787c9d266184 | 1416
2018-08-10 |  |  |  | 905fe2ffb2e649ac8ce1971a26c87f79b748275e | 1470
2048-08-14 |  |  |  | ef9d4638bc6ada6418f30eeb7359020e577cde12 | 1468 &1422
2048-08-14 |  |  |  | 6cb446702a0aca0ee8cacdf891bb0131f3d38c0e | 1470
2018-08-18 |  |  |  | e0e2605724c01d49df775b94d4523b3638bc99f5 |  | ..
2018-08-19 |  |  |  | ff119a6c78df645c2a1e3456e1057e7ea99d99f1
Srinivas Nangana | 19th August 2018 |  | . | No
2018-08-19 |  |  |  | 1d166b0bd283fc04893b81998cdb57fb0d1c1c55 | 1499 | no
2018-08-20 |  |  |  | 28f295f1a59ffac1050b68dd33d3b223a627ff95 | 1511 | no
2018-08-20 |  |  |  | f4991d933e82243c26ebb317274a87ad31e977d3 | 911 | no
2108-08-21 |  |  |  | fd3a3ae6c0635a84938b6db6aa9a60f2e1a22a0f
Ram Mohan Reddy | 21st August 2018 |  | DB changes need
2018-08-24 |  |  |  | e7c29dae068aabd3a5d97167605ae93a224525cd | No
Added digital board functionality | Srinivas Nangana |  | 27th August 2018 | No | No
2018-08-25 |  |  |  | 0e6570fa4419e136c81d14f6c08c252bfa2a573f | ONE-I1544,
ONE-T901,
Excel Report Functionality and pharmacy consolidate Report | Tejaswi Terala |  | 27th August 2018 | OPD(No need to do
No
2018-08-25 |  |  |  | 41f03893c9fa30eb5f6d2e81341c25b8d335b8ff | 881
Tejaswi Terala | 27th August 2018 |  | No | No
31/08/2018 |  |  |  | b54e59ad311e5492dfa6962f851f7749357d8c49 | 1531 and 1450 | No need DB Changes
31/08/2018 |  |  |  | 28a0dccd93544b2f9491819dbb1cf690ed755d16 |  | Db changes need
Communication need
Yes
2018-09-01 |  |  |  | bd96b6edc203de1897ec32d12797a502729321f1 |  | No Need
2018-09-02 |  |  |  | 8432643d3242f11b30ed661fe312d96eb96f8107
Counselling,Diagnosis wise Search with Emr,Dyanmic tabs, OPD status | Ram Mohan Reddy ,
8th September 2018 | Need Db changes in Opd.patient_visit_trans and emr.org_tab_speciality_xref
| queries and application properties need to move |  | Billing, IPD, OPD
2018-09-02 |  |  |  | 684c7eebe91f93093e6a13cc8598acf3eb154712 |  | no
2018-09-01 |  |  |  | bc20942149ee0135fcfa39faaf85571dd750b552 |  | No
2018-09-05 |  |  |  | 684c7eebe91f93093e6a13cc8598acf3eb154712
2018-09-05 |  |  |  | d6b2a90a7cf9018a327deec2fde16cd493c72e55 | 1589
2018-09-05 |  |  |  | bd10e0438b270cbb5b2685412459231c8dcb3a49
2018-09-09 |  |  |  | e54507ce2063387775ada900b51f1b4cea73f170 | 1589
2018-09-09 |  |  |  | 89393d78e7aa98b8dd95331780621e1dcf7880c6 | 1589
2018-09-09 |  |  |  | dfe9278028304c3c850efb76b978f404b0879bca | 1600
2018-09-09 |  |  |  | 529404ccccbb880bc9f1db8698df78323bb22baa
Date(MM/DD/YYY) |  |  |  | Commit Id | Bug Ids
DB Changes | S3 Bucket |  | Config server
Dependency
Templates

## JAVA TAGS
S.NO | MODULE NAME | QA TAG | PROD TAG
1 | OPD | QA_2.10.30_DEC28 | PROD_2.10.30_DEC28
2 | OPD | QA_2.10.31_JAN04 | PROD_2.10.31_JAN04

## Java-2019
Release Track
Sl. No | Date (MM/DD/YYY) | Developer Name & branch name | Module Name | QA Tag | QA Commit Id | Bug Ids | Task Ids | Remarks | Production Release Dt | Prod Tag | Prod Commit id | DB Changes | S3 Bucket | Config server Queries | Dependency Jars | Templates | New Environmental Variables Used
1 | 2019-01-02 | SIREESHA .K/T1183 | EMR |  |  | NO | T1183 | NURSE WAITING ROOM FUMCTIONALTY | 04th January 2019 |  |  | YES | NO | YES | NO | NO | NO
2 | 2019-01-04 | Tejaswi/Dev | OPD | QA_2.10.31_JAN04 | 26a3fc61d9f326e84ebe9c550548607f47489039 | 2498 | No | Patient status bug fix(Order by issue) | 04th January 2019 | PROD_2.10.31_JAN04 | 8c7efbaea20af42d8ab98cd1a96a2e00da3445b7 | No | No | No | No | No | No
3 | 2019-01-10 | Tejaswi/srinivas/jwt-tokens | Admin |  |  |  | T425,T889 | Converted to new arch and sessions related Apis |  |  |  | Yes | No | Yes | Zuul | No | Need to change script to new arch
4 | 2019-01-12 | Chaitanya | Pharmacy |  |  | ONE-I2391,ONE-I2350,ONE-I2292,ONE-I2291,ONE-I2290,ONE-I2288,ONE-I2286 | ONE-T1128 | Added discount in pharmacy vendor invoice |  |  |  | Yes | No | Yes | Reports
5 | 2019-01-12 | manmadha/MIS-T1161 | Reports |  |  |  | ONE-T1223 | Chnaged Pharmacy Returns Slip page orientation from landscape to portrait. |  |  |  | No | No | No | No | No | No
6